## Project schedule
| CIVE 202 Project #3 | Project Members |  |  |  |  | Project start: | [7 empty] | 2026-04-01 | [9 empty] | Project End: | [7 empty] | 2026-04-21
| VISUALIZE | Michael McCarthy, Fatima Davila, Harrison Drake |  |  |  |  | Display week: | [7 empty] | 1
SIMPLE GANTT CHART by Vertex42.com
| https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html | [5 empty] | 2026-03-30 | [6 empty] | 2026-04-06 | [6 empty] | 2026-04-13 | [6 empty] | 2026-04-20 | [6 empty] | 2026-04-27 | [6 empty] | 2026-05-04 | [6 empty] | 2026-05-11 | [6 empty] | 2026-05-18
| TASK | ASSIGNED TO | PROGRESS | START | END | time axis 2026-03-30 to 2026-05-24
 | time axis 2026-03-30 to 2026-05-24
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Planning for function development
| Research NRI definition of risk to create our own risk definition | Fatima | 100% | 2026-04-01 | 2026-04-01 | 1
| Plan custom risk calculations | group | 100% | 2026-04-02 | 2026-04-02
| Research Geopandas plotting options | Group | 100% | 2026-04-03 | 2026-04-03
| Develop methods for the final report | Group | 100% | 2026-04-04 | 2026-04-04
|  | Group | 100% | 2026-04-05 | 2026-04-06
|  | Group | 100% | 2026-04-07 | 2026-04-11 | 5
Draft functions in Python
| Merge datasets for analysis | Michael | 100% | 2026-04-06 | 2026-04-07 | 2
| Clean Datasets | Group | 100% | 2026-04-08 | 2026-04-09 | 2
| Create functions in Python for a custom risk score | Group | 100% | 2026-04-10 | 2026-04-11 | 2
| Generate Summary Table for Analysis | Group | 100% | 2026-04-12 | 2026-04-13
| Generate Map plots using Geopandas | Group | 100% | 2026-04-13 | 2026-04-15
Execution
| Data cleaning and Processing | Group | 100% | 2026-04-15 | 2026-04-16
| Testing and validation | Group | 50% | 2026-04-17 | 2026-04-18
| Written Technical Report | Group | 100% | 2026-04-15 | 2026-04-18
| Annotated Code Document (ACD) | Group | 0% | 2026-04-06 | 2026-04-20
| Scope of Work (SOW) | Group | 100% | 2026-04-04 | 2026-04-09
| Final Project integration and submission | Group | 0% | 2026-04-19 | 2026-04-21
Evaluation
| Monitor progress | Group | 80% | 2026-04-01 | 2026-04-20 | 20
| Task #3 Track Billable Hours | Group | 90% | 2026-04-01 | 2026-04-20
| Evaluate progress | Group | 80% | 2026-04-06 | 2026-04-20 | 15
| Gather feedback | Group | 0% | 2026-04-21 | 2026-04-26 | 6